## Introduction
Engagement planning template
Introduction This template is to help programmes at place and across the ICS to plan their engagement activities for how they work with people and communities. The ICS has developed a Working with People and Communities strategic framework which was agreed by the Integrated Care Board in July 2022. This outlines our ambition for how we work with people and communities including the need to: - Build relationships and trust with communities - Make engagement accessible and exciting - Co-ordinate engagement better across south east London - Go out to communities and bring the conversation closer to people - Recognise the impact engagement has on people The ICS vision and mission for working with people and communities: Working with local people to build a healthier future for all communities across south east London. The South East London ICS works in partnership with local people and communities. This improves health and wellbeing and supports people to thrive and live healthier lives. We will prioritise working in partnership to address health inequalities; these are unfair and systematic differences in health between different groups of people. Tools to support engagement This engagement planning template forms part of the engagement toolkit which has been developed to support programmes in developing their engagement in line with the strategic framework and responsibilities around engagement. Have a look at the toolkit, guides and tops tips and have an initial conversation with the engagement team before filling in this template and discussing further with the engagement team. Contact the ICS engagement team, read the engagement toolkit and fill in the engagement planning checklist at the earliest stage of planning your project. This helps you maximise the value of working with people and communities for your programmes.

## Engagement checklist
Please use the green boxes to fill in
Engagement checklist
Checklist | Yes/No | Comment
What is the purpose of engagement in your project?
Can local people influence your work? Please explain how they can influence your work.
If your answer is no to above, consider what information may need to be shared with local people and communities.
If your answer is yes, please indicate below, the purpose of your engagement by answering Yes/No and include brief comments | Yes/No | Comment
Gather intelligence and insight
Understand people’s views, experiences and aspirations
Understand how current services are performing/ could be improved
Test and shape some ideas you already have
Redesigning services/ pathways
Design something from scratch
Inform a decision
Identify priorities or discuss tricky trade offs
Make a significant change to services (like closing, moving or changing the way services are delivered) Legal duty is triggered consult the Engagement tool
Something else….please describe in the comment box

## Planning phase
Please use the green boxes to fill in
Engagement planning template
Name of project:
Project lead:
Project engagement lead (if different from project lead):
1.Plan
1.1. Project overview
Key points | Comments
What is the aim of your project?
What is the aim of your engagement activity?
What is the timeline of the project and when does a decision need to be made?
What can local people influence and what is fixed?
1.2. Existing insight: what do you already know?
NOTE: Before you start planning your engagement activity, think about what we already know in the system which is relevant to your project. This will help focus your project and engagement activity on any gaps in insight, who you may need to engage with and help shift engagement activity to working with people and communities to actively contribute to identifying soluctions within your proposals for service design . Look at the insight pages of the toolkit about existing sources of insight and then outline what you already know.
Key points | Comments
What we already know?
What we need to find out?
1.3. Equality Impact Assessment (EIA)
NOTE: You need to carry out an EIA as part of your proposals. You should do this at the beginning of your project and update it after the engagement has taken place before any decisions are made. Read the EIA pages of the toolkit here for more information. Contact the Equality Diversity and Inclusion (EDI) team for support and access to the EIA toolkit. Read the ICS EIA toolkit for further information and guidance in carrying out an EIA.
Key points | Comments
Which communities does your EA highlight that you need to hear from?
Which groups of people will be affected by your project? Either positively or negatively?
1.4 Who are you planning to engage?
NOTE: Enlist the people and communities you want to engage in your project. Think about communities not accessing services and who experience the greatest health inequalities. Look at the engaging with people from under-served communities in the toolkit. You may find it useful to map your stakeholders according to their interest and influence to help you prioritise your engagement activity. For more details see How to ... understand who to speak to (mapping your stakeholders) and have a look at the toolkit.
Key points | Comments
Who is directly affected by your proposals?
Who is indirectly affected by your proposals?
Are there people with particular lived experience that you need to hear from and work with?
Whose voice might be missing? Are there particular communities you want to hear from and work with? Think about gaps in insight from section
NOTE: You may find it useful to map your stakeholders according to their interest and influence to help you prioritise your engagement activity. For more details see How to ... understand who to speak to (mapping your stakeholders) and have a look at the toolkit.

## Engage phase
Please use the green boxes to fill in
Engagement planning template |  | Webinars/ conferences | Newsletter
Name of project: | 0 | Survey (online and/or hard copy) | Letters to patients
Project lead: | 0 | Community engagement/ outreach | Emails to patients
Project engagement lead (if different from project lead): | 0 | 1:1 interview/conversations | Posters
|  | Focus group/ workshop | Leaflets
2. Engage |  | Working with those with lived experience | Flyers
2.1 Methods |  |  | Summary reports
NOTE: Depending on what the purpose of your engagement are different engagement methods might suit your project better. Think about the methods you will use to engage people and why. You will need to identify the resources you have available such as budget and staff to will help inform the methods you use. Using a number of different engagement methods will mean you are more likely to hear form a wider group of people. Qualitative methods (such as interviews, group discussions or online chat forums) are better for more exploratory conversations, or when you are trying to answer the question ‘why’. Quantitative methods such as surveys and polls, are better placed to answer questions like “how many” and “how often” and assessing levels of agreement and disagreement with what is proposed. We have a range of tools to support your programme in engaging with local people and communities, including: Think about your engagement aims and objectives and have a look at the engagement continuum in the engagement toolkit to help identify which methods of engagement will work best for your project. The methods section of the toolkit will also help you identify different methos to use. It is often best to use a combination of methods. We have a range of tools in place to support the methods you are using. Accessibility How have you made engagement activities accessible for those you’re trying to reach? Accessible might mean physical access (to a meeting room/ online session or the need for interpreters) as well as psychologically accessible (for those with a learning disability or who have experienced significant trauma) as well as people who are digitally excluded and cannot giver their views through on-line methods. |  |  | Other
Enlist engagment methods you are planning to use | Comments
2.2 Engagement questions
Key points | Comments
What do you need to know from people?
What questions will you ask to find this out? NOTE:You will need to structure questions differently for different engagement methods such as focus / discussion groups, chat forums or surveys. Read the how to have individual conversation guide which also includes a template conversation topic guide. Read the how to develop effective survey questions guide if you are developing a survey which will help you developed focused and specific questions which will provide answers that will be helpful to you.
How will you capture and record insight?
2.3 Language and communication
NOTE: Remember to provide information in plan and clear English. See the communication section of the engagement toolkit for some tops tips on how to do this.
Enlist the written materials that you are planning to use | Comments
2.4 Timescales
Key points | Comments
What needs to happen? Outline your timeline and key milestones
NOTE: As you deliver engagement activity keep a record - you may find the activity template in next tab a useful tool to record your activity. If you have a project page on let’s talk platform you can keep this up to date with activity, themes and how you are using this insight so you can tell your engagement story and the difference you are making.

## Analysis & feedback phase
Please use the green boxes to fill in
Engagement planning template
Name of project: | 0
Project lead: | 0
Project engagement lead (if different from project lead): | 0
3 Analysis and feedback
3.1.Who/ How
Key points | Comments
How will you analyse the insight you receive?
Who will you analyse the insight you receive?
Who will you involve?
How does this affect decision making?
Where is the final decision made? NOTE: Be open and transparent about where and when decisions are made as part of your feedback to people who took part.
How will you feed back to people who have been involved? NOTE: Look at the analysis and feedback pages of the toolkit for top tips.

## Evaluation phase
Please use the green boxes to fill in
Engagement planning template
Name of project: |  | 0
Project lead: |  | 0
Project engagement lead (if different from project lead): |  | 0
4 Evaluation
3.1.Who/ How
Key points | Comments
How will you know you have achieved your engagement objectives?
How will you evaluate your process, progress and impact?
How will you gain the views of people involved in the process?
NOTE: Use the How to ... evaluate engagement activities to think about your own measures of success.

## Activity planning & log
Please use the green / pink boxes to fill in | [13 empty] | Planned
On-going
Engagement planning template | [13 empty] | Delivered
Name of project: |  | 0 | [11 empty] | TBC
Project lead: |  | 0 | [11 empty] | Closed
Project engagement lead (if different from project lead): |  | 0
4. Activity planning
You may find it useful to identify your engagement activity in the following table:
Engagement activity | Purpose | Messages / questions | Where? | When? | Lead | Resources / materials needed | How being promoted? | Other comments | Status | Participants attending / demographic | Number participants | Key points comments /recommendations | Follow up actions